Reedley College Assessment Timeline

Fall 2007:

- All Reedley College course outlines have been modified to include course student learning outcomes

Fall 2008:

- A Student Learning Outcomes Coordinator is assigned

- Joint Program Review and Curriculum ad-hoc committee draft Institutional Learning Outcomes

Spring 2009:

- The Student Learning Outcomes Coordinator takes over as Program Review Chair

- Proposed Institutional/GE Learning Outcomes are presented to Reedley College during Duty Day Presentations

- Senates approve Institutional/GE Learning Outcomes

- College Council approves Institutional/GE Learning Outcomes

- Program Review Cycle 3 Handbook draft is completed

- Senates approve Program Review Cycle 3 Handbook

- College Council approves Program Review Cycle 3 Handbook

- Assessment Advisory Committee formed (ad-hoc of College Council)

Fall 2009:

- Assessment Advisory Committee drafts the Course and Program Assessment Reporting Forms

- Senates approve Course and Program Assessment Reporting Forms

- Begin mapping courses to GE Learning Outcomes

- Programs begin Cycle Three of Program Review

Spring 2010

- Program Review Cycle Two is complete along with program learning outcomes

- Assessment of all Learning Outcomes begins for RC and NC

- Begin mapping Course Student Learning Outcomes and Program Learning Outcomes to GE Outcomes

- Begin mapping degree and certificated program outcomes to GE Outcomes

- Develop matrix to map non-instructional programs to Institutional Learning Outcomes

Fall 2010

- All Program Outcomes mapped to GE or Institutional Outcomes

- Assessment and analysis of programs and courses continued

- Program and course begin implementing recommendations based on assessment

- Begin mapping non-instructional Program Learning Outcomes to Institutional Learning Outcomes

Spring 2011

- Assessment, recommendations, and implementation based on recommendations 50% complete

Fall 2011

- Assessment, recommendations, and implementation based on recommendations 75% complete

Spring 2012

- Assessment, recommendations, and implementation based on recommendations 100% complete

Fall 2012

- Assessment, recommendations, and implementation based on recommendations 100% complete