**Draft Timeline for SCCCD Strategic Plan**

District Timeline runs from Fall 2012 – Fall 2016

College Timeline run from Fall 2013 to Fall 2017

**District Only**

|  |  |  |
| --- | --- | --- |
| March 2011 | Survey for minor updatesTimeline Created | District |
| April 2011 | 1st Draft | District |
| May 2011 | Final Draft | District |
| June 2011 | Board approval of timelineAnd final draft which includes minor revisions | District |
| Aug. - January 2012 | Preparation for comprehensive assessment (Charette) and full revision process. Gather data from all areas internal and external scans.  | District |
| February 2012 | Charette & all survey information gathered | District |
| April 2012 | 1st Draft | District |
| May 2012 | Final Draft |  |
| June 2012 | Board approval of Strategic Plan for District | District/Board |
| July 2012 | Implementation of new District Strategic Plan | District |
| Aug. – January 2013 | Annual scan for District (1st year) | District |
| March 2013 | Summary of results from annual scan, report of progress, if changes are pertinent minor revisions made if not just report to Board | District |
| June 2013 | Annual report to Board on District Strategic Plan | District/Board |
| Aug. – January 2014 | Annual scan for district (2nd year) | District |
| March 2014 | Summary of results from annual scan, review of results from 1st year report, recommended changes made to the Board. (these are minor updates)  | District |
| June 2014 | Minor revisions/updates to the District Strategic Plan are presented to the Board | District/Board |
| July 2014 | Implementation of changes to District Strategic Plan | District |
| Aug. - January 2015 | Annual scan for District (3rd year) | District |
| March 2015 | Summary of results from annual scan, review of results from 1st year report, recommended changes made to the Board. (these are minor updates)  | District |
| June 2015 | Minor revisions/updates to the District Strategic Plan are presented to the Board | District/Board |
| July 2015 | Implementation of changes to District Strategic Plan  | District |
| Aug. - January 2016 | Preparation for comprehensive assessment (Charette) and full revision process. Gather data from all areas internal and external scans. (4th year) | District |
| February 2016 | Charette & all survey information gathered | District |
| April 2016 | 1st Draft | District |
| May 2016 | Final Draft |  |
| June 2016 | Board approval of Strategic Plan for District | District/Board |
| July 2016 | Implementation of new District Strategic Plan | District |

**Colleges and Centers ONLY**

|  |  |  |
| --- | --- | --- |
| **Date** | **Duties** | **Area** |
| June 2012 | District Strategic Plan is approved | Board/District |
| Aug. – January 2013 | Colleges/centers prepare for comprehensive assessment, Charette, internal and external scans. Colleges/centers will develop college/center strategic plans that include the District Strategic Plan goals. | Colleges |
|  February 2013 | Charette, all survey information gathered | Colleges |
| March 2013 | 1st Draft | Colleges |
| May 2013 | Final DraftPresentation to appropriate constituency groups | Colleges |
| June 2013 | Board presentation of Strategic Plan for each college/center | College/Board |
|  July 2013 | Implementation of College/ Center Strategic Plans | Colleges |
| Aug. – January 2014 | Annual Scan for Colleges (1st year) |  |
| March 2014 | Summary of results from annual scan, report of progress, if changes are pertinent minor revisions made if not just report to College Council | Colleges |
| May 2014 | Reports to constituency groups and College Council | Colleges |
| Aug. – January 2015 | Annual scan for Colleges/Centers (2nd year) | Colleges |
| March 2015 | Summary of results from annual scan, review of results from 1st year report, recommend changes to the board. (minor revisions) | Colleges |
| May 2015 | Changes given to constituency groups, College Council and the Board | Colleges/Board |
| June 2015 | Board approval  | Board |
| July 2015 | Implementation of modified College/Center Strategic Plans | Colleges |
| August 2015 – January 2016 | Annual scan for Colleges/Centers (3rd year) | Colleges |
| March 2016 | Summary of results from annual scan, report of progress, if changes are pertinent minor revisions made if not just report to College Council | Colleges |
| May 2016 | Changes or report given to College Council and constituency groups. | Colleges |
| June 2016 | District Strategic Plan is approved | Board/District |
| August 2016 - January 2017 | Preparation for comprehensive assessment (Charette) and full revision process. Gather data from all areas internal and external scans. (4th year) Colleges/centers prepare for comprehensive assessment, Charette, internal and external scans. Colleges/centers will develop college/center strategic plans that include the District Strategic Plan goals. | Colleges |
|  February 2017 | Charette, all survey information gathered | Colleges |
|  March 2017 | 1st Draft | Colleges |
|  May 2017 | Final Draft Presentation to appropriate constituency groups | Colleges |
|  June 2017 | Board presentation of Strategic Plan for each college/center | College/Board |
|  July 2017 | Implementation of College/Center Strategic Plans | Colleges |

**Approved by Strategic Planning Work-group on April 15, 2011, Reviewed and approved on April 29, 2011**