## Slide 1: Accreditation
Comprehensive Evaluation Visits October 2011

## Slide 2: Accreditation Liaison Officers
Fresno City College – Tony Cantu
Reedley College – Marilyn Behringer
North Centers – Deborah Ikeda

## Slide 3: Accreditation Timeline for FCC
Steering Committees Formed | October 2009
Substandard Committees Formed | January 2010
Data Collection - Survey faculty/staff/students GAP Analysis and Review | April-May 2010
1st draft submitted to campus constituency for review | October 2010
Campus Forums/Workshops | November 2010
2nd draft submitted to campus constituency for review | January 2011
Begin validation, finalization and constituency approval | February-March 2011
Self-study completed and sent to Chancellor | May 2011
Submit for Board Review | June 2011
Board of Trustees approval | July 2011
Pre-team site visit | August 2011
Report submitted to visiting team and commission | August 2011
Team visit | October 2011
Commission Meets | January 2012
Recommendations Published | February 2012

## Slide 4: Fresno City College Accreditation Committees
Accreditation Steering Committee Co-Chairs
Tony Cantu, John Fitzer, Ruthina Estrada, Sergey Saluschev (4)
Standard I − Institutional Mission and Effectiveness — Peg Mericle, Bob Boyd, Kelli O’Rourke(3)
Mission
Improving Institutional Effectiveness
Standard II − Student Learning Programs and Services (9)
Instructional Programs — Michael Roberts, Maggie Taylor, Leticia Murrietta
Student Support Services — Chris Villa, Yuri Kostin. Vacant
Library and Learning Support Services — Jim Tucker, Ray Sanchez, Vacant
Standard III − Resources (12)
Human Resources — Jothany Blackwood, Daniel Himes, Michael Hopkins
Physical Resources — Cheryl Sullivan, Jeannie Koshear, Richard Kilgore
Technology Resources — Monique Kelley, Roberta Baber, Harry Zahlis
Financial Resources — Michael Guerra, Marianne Dunklin, Shanna Ahrens
Standard IV − Leadership and Governance — Cynthia Azari, Bruce Hill, Tammy Maddox (3)
Decision-Making Roles and Processes
Board and Administrative Organization

## Slide 5: Accreditation Timeline for Reedley & North Centers
Steering Committees Formed | January 2010
Substandard Committees Formed | February 2010
Data Collection - Survey faculty/staff/students GAP Analysis and Review | April-May 2010
1st draft submitted to campus constituency for review | August 2010
Campus Forums/Workshops | August 2010
2nd draft submitted to campus constituency for review | January 2011
Begin validation, finalization and constituency approval | February-March 2011
Self-study completed and sent to Chancellor | May 2011
Submit for Board Review | June 2011
Board of Trustees approval | July 2011
Pre-team site visit | August 2011
Report submitted to visiting team and commission | August 2011
Team visit | October 2011
Commission Meets | January 2012
Recommendations Published | February 2012

## Slide 6: Reedley College Accreditation Committees
Accreditation Steering Committee Co-Chairs -- Marilyn Behringer, Anna Martinez (2)
Standard I − Institutional Mission and Effectiveness —
Barbara Hioco, Eileen Apperson-Williams, Linda Nies (3)
Mission
Improving Institutional Effectiveness
Standard II − Student Learning Programs and Services -- Marilyn Behringer, Anna Martinez (2)
Instructional Programs — Marilyn Behringer, Anna Martinez, Lisa McAndrews
Student Support Services — Monica Cuevas (NC), Mario Gonzales, Michael White
Library and Learning Support Services — Stephanie Curry, Cynthia MacDonald (NC)
Standard III − Resources -- Scott Thomason, Gary Sakaguchi
Human Resources — Melanie Highfill, John McPhee (NC), Gary Sakaguchi, Scott Thomason
Physical Resources — Scott Thomason, Jim Burgess
Technology Resources — Gary Sakaguchi
Financial Resources — Scott Thomason, Melanie Highfill
Standard IV − Leadership and Governance — Brian Shamp (NC), Bill Turini, Tom West
Decision-Making Roles and Processes
Board and Administrative Organization

## Slide 7: North Centers Accreditation Committees
Accreditation Steering Committee Co-Chairs
Standard I − Institutional Mission and Effectiveness —
Mission
Improving Institutional Effectiveness
Standard II − Student Learning Programs and Services
Instructional Programs —
Student Support Services —
Library and Learning Support Services —
Standard III − Resources
Human Resources —
Physical Resources —
Technology Resources —
Financial Resources —
Standard IV − Leadership and Governance —
Decision-Making Roles and Processes
Board and Administrative Organization

## Slide 8: Recommendations from 2005
SCCCD | Fresno City College | Reedley College
 | Participatory Governance | Student Learning Outcomes
 | Program Review | Institutional Planning
 | Integrated Planning | Dialogue
 | Library Collection | Program Review
 | Strategic Planning Process | Library and Learning Resources
Strategic Planning Connection with Colleges Strategic Planning | College Strategic Planning Connection with District Strategic Planning | College Strategic Planning Connection with District Strategic Planning

## Slide 9: District Role in Accreditation
Facilitate and support the successful implementation of the college’s strategic plan
Describe/display/evaluate the particular ways functions are distributed in the organization
Communicate with the Governing Board regarding accreditation and obtain their approval of the final report
Share the team report with the Board, district and college staff.