**Reedley College Program Review Recommendations\* Annual Progress Report**

**(\*“Recommendation” changed to “Goals” beginning Cycle Three)**

**Program: Reedley College Library Year: 2011-2012 Contact: Stephanie Curry**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Recommendation\***(as appropriate, identify the campus where the recommendation applies) | **Proposed Timeline** | **Activities/Facilities/ Curriculum/Equipment Necessary to Accomplish Recommendation\*** | **Resources Needed, Include Estimate Costs** | **Status** | **Outcome**  |
| RC\_Maintain and Increase classified staffing at the Reedley College Library. Replace certificated librarian in the event of retirement. | **Continuous**  |  | **Part time Librarian at Madera Center**  | **With North Center’s librarian moving to Willow starting Fall 2012 need will need a librarian at Madera**  | **Need to examine librarian coverage for Madera Center or Fall 2012.** |
| RC\_Hire a full time or adjunct certificated librarian to coordinate online services for students | **2014** | **We will look for grant opportunities for this recommendation**  |  | **No progress on the recommendation library decided to concentrate on information competency**  | **No Change** |
| RC\_Update and expand print and audio visual materials | **Continuous**  | **Maintaining Current Funding**  |  | **Library continues to expand collection both in print and with online materials.**  | **Status Quo** |
| RC\_Increase information literacy opportunities for students on campus and remotely | **2011** | **Maintain access to LRC 104 for Information Competency Presentations.**  |  | **Instructional Librarian is offering several types of library instructions. New curriculum LIBSKLS 1 offered for the first time**  | **Instructional Librarian has increased the number of BI’s and the number of instructors who request a BI. LIBSKLS 1 class offered for the first time** |
| RC\_Expand Library Services for Distance Education Students | **2014** | **Add tutorials to web page** |  | **Online information competency tutorials reviewed**  | **Library website update and posted videos Summer 2012 project** |
| RC\_Identify funds to maintain subscriptions to Online Databases and E-books | **2011** | **Funds to maintain database subscriptions**  |  | **Title V Grant pays for a portion of the library databases**  | **Library received around $17,000 from Title V for databases**  |
| RC\_Purchase Resources and Expand Services for Basic Skills Students and other targeted populations | **2011-2014** | **Adding the library to future grants to fund library resources and services for targeted populations**  |  | **Part of the Title V grant focuses on expanding library resources for basic skills students**  | **256 Basic Skills books have been purchased through the grant**  |
| RC\_Create new information access opportunities for students using technology | **2011-2014** |  |  | **The Title V grant also includes a laptop loan program we have received 16 laptops** | **The library will begin its laptop loan program in Summer/Fall 2012** |

1. Provide any additional changes made to the program that were not a part of your program review report.

The library offered for the first time in Spring 2012 LIBSKLS 1 a basic information competency class that can be taught on campus as well as online. This class was articulated to CSU Fresno.

1. List in detail any new program needs and a brief rational for this need.
2. Summarize the progress your program has made this year on SLO assessment.

After reviewing our SLO data last year librarians for RC and NC revised the assessment tool, with assistance from the institutional researcher. The goal was to make the questions more clear and effective. It was decided to pilot the new form at RC during the Spring 2012 semester to see if it would garner the data that we required. We could not test it at the NC due to the extended medical leave of the NC librarian in Spring 2012. Librarians will review the data in April 2012. If the data proves the assessment tool valid we will assess Library Instruction again in Fall 2012 at all locations. If not we will again revise the assessment tool.

1. Provide any additional information that your program would like to share.

Starting in Fall 2012 the current North Centers Librarian will be moved permanently to the Willow International site. This move leaves the need for a librarian to staff the Madera Center library at least part time.